## Team Members
Enter the First Name of Each Team Member
Abdulziz alqahtani
Ahmed aldayel
Faisal Batis
Khaled tomihi
abdullah Bin Suqaih

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
| S | first meeting | project discussion with the team | discussion with the team about the project and tasks dividing and share the Scrum file to the team | 3-low | Done
| S1 | Phase 1 | phase 1 discussion | tasks dividing and create document for phase 1 | 2-medium | Done
| S2 | second meeting | discussion about the idea of the app | we discussed about the idea of the game. how it works, how to make the levels of the game more challenging, the kind of challenges of each level. So its the overall structure and idea of the game. | 2-medium | Done
| S2 | The application interface | the design of the app | as a team we designed the interface of the game as an prototype design so we can edit it in the future. | 2-medium | Done
| S2 | features and fucntionalities | we discussed about the features and fucntionalities that we need to build for the app | the game is testing the information of the user by listing some MCQ questions in a quiz. And the questions are divided into levels, each level has it category of questions and the levels vary with the difficulity. the app has a scoring system by which you get points by answering right answers and none by answering wrong. Also you can sign up and sign in before you start the quiz. | 1-high | Done
| S3 | coding | learning about the flatter coding language | we started to learn the flatter languge to implement the code and to build the app | 2-medium | Done
| S3 | coding 2 | app development | we started to develop the app | 3-low | Done
| S4 | revision | discussion about the overall work we have completed so far | discussion about the overall work we have done so far and check if we need to edit something or add more features | 3-low | Done
| S5 | Phase 2 meeting | viewing the phase 2 requirments | we took a look together on the phase 2 requirments and we identified what we need to work on in phase 2 | 3-low | Done
| S5 | Phase 2 second meeting | discussion about phase 2 | we discussed about the Phase 2 and we build a plan for phase 2 and we divided the work on each team member | 2-medium | Done
| S6 | the prototype | the structure of the levels | we choose to put three levels in the prototype and we identified the overall content of the levels | 2-medium | Done
| S6 | the prototype | start building the prototype | in the begining we specfied the features that we will put in the prototype then we started coding and developing the prototype | 1-high | Done
| S7 | System models | learning about all models(diagrams) | we started to learn about all the models(diagrams) that we need to design | 2-medium | Done
| S7 | System models 2 | designing the models | we designed the system model during several periods of time and finished all the 6 models | 1-high | Done
| S8 | phase 2 revision | discussion about the overall work we have completed so far | discussion about the overall work we have done so far and to make sure that all the models are well designed | 3-low | Done
| S9 | Phase 3 meeting | viewing the phase 3 requirments | we took a look together on the phase 3 requirments and we identified what we need to work on in phase 3 | 3-low | Done
| S9 | Phase 3 plan | making a plan to finish phase 3 | we discussed about phase 3 requirments and we divided the work into multiple tasks and we assigned each task to a team member | 3-low | Done
| S10 | The second version of the app | developing the second version of the app | we started developing the app to meet more requirments and we add several features and levels to the app | 2-medium | Done
| S10 | reviewing the second version | we reviewed discussed about the second version of the app | we tested the second version and we figured out what are the problems in it and what are the functions and features we need to add to the app to make it better | 2-medium | Done
| S10 | the final version of the app | developing the final version of the app | after we made the second version and reviewing it we figured out what are the updates we need to do to it and we started building the final version with all the requirments and features we wanted | 1-high | Done
| S11 | completing the documentation | writing all the documentation required in the phase 3 | we made the summary for the three phases and we build the (MVC) pattern and the layered architecture and all the things required from us in a document | 1-high | Done
| S11 | uploading the project to github | we uploaded the project to github as required | after uplodaing the project to github we add the link of it in the document | 2-medium | Done
| S12 | creating the powerpoint | we created the powerpoint presentation for the project | we summarized all the procces of building the project in the powerpoint presentation and we prepared for the project discussion | 3-low | Done
| S13 | final revision | we reviewed the whole project | we reviewed the final version of the app, the document, the powerpoint presentation and we made sure everything is completed | 1-high | Done
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| developing the second version of the app | 10 | 11 | Abdulziz alqahtani | Done | 2024-01-26 | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-01-26 | 10 | 10 | 83 | 93
| reviewing the second version of the app | 4 | 4 | Ahmed aldayel | Done | 2024-01-28 | Start Date: | 2024-01-26 | Abdulziz alqahtani | 22 | 22 | 100% | 2024-01-27 | 0 | 10 | 83 | 86.3571
| developing the final version of the app | 5 | 7 | Ahmed aldayel | Done | 2024-01-30 | Sprint Length | 14 | Ahmed aldayel | 19 | 19 | 100% | 2024-01-28 | 4 | 14 | 79 | 79.7143
| developing the final version of the app | 5 | 5 | Faisal Batis | Done | 2024-01-30 | Hours Per Day: | 6.6429 | Faisal Batis | 22 | 22 | 100% | 2024-01-29 | 0 | 14 | 79 | 73.0714
| developing the final version of the app | 5 | 6 | Abdulziz alqahtani | Done | 2024-01-30 |  |  | Khaled tomihi | 15 | 15 | 100% | 2024-01-30 | 15 | 29 | 64 | 66.4286
| reviewing the final version of the app | 8 | 8 | Khaled tomihi | Done | 2024-01-31 |  |  | abdullah Bin Suqaih | 15 | 15 | 100% | 2024-01-31 | 8 | 37 | 56 | 59.7857
| creating the powerpoint presentation | 10 | 11 | abdullah Bin Suqaih | Done | 2024-02-01 |  |  |  | 0 | 0 | 0% | 2024-02-01 | 15 | 52 | 41 | 53.1429
| adding more content to the powerpoint presentation | 5 | 5 | Ahmed aldayel | Done | 2024-02-01 | [6 empty] | 2024-02-02 | 13 | 65 | 28 | 46.5
| reviewing and editing the powerpoint presentation | 7 | 8 | Khaled tomihi | Done | 2024-02-02 |  |  | Total: | 93 | 93 | 100% | 2024-02-03 | 14 | 79 | 14 | 39.8571
| craeting the layered architecture and the (MVC) pattern | 6 | 6 | Faisal Batis | Done | 2024-02-02 | [6 empty] | 2024-02-04 | 14 | 93 | 0 | 33.2143
| documentation | 7 | 8 | Faisal Batis | Done | 2024-02-03 | [6 empty] | 2024-02-05 | 0 | 93 | 0 | 26.5714
| documentation | 7 | 7 | Abdulziz alqahtani | Done | 2024-02-03 | [6 empty] | 2024-02-06 | 0 | 93 |  | 19.9286
| adding the project to github | 5 | 7 | abdullah Bin Suqaih | Done | 2024-02-04 | [6 empty] | 2024-02-07 | 0 | 93 |  | 13.2857
| final revsion | 5 | 5 | Ahmed aldayel | Done | 2024-02-04 | [6 empty] | 2024-02-08 | 0 | 93 |  | 6.6429
| creating the scrum | 4 | 4 | Faisal Batis | Done | 2024-02-04 | [6 empty] | 2024-02-09 | 0 | 93 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 83 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 83 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 79 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 79 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 64 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 56 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 41 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 28 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 14 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Determine the whole structure of the prototype and the features it will have | 3 | 4 | Abdulziz alqahtani | Done | 2024-01-15 | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-01-15 | 6 | 6 | 58 | 64
| Making the overall content and design of the three levels | 3 | 3 | Faisal Batis | Done | 2024-01-15 | Start Date: | 2024-01-15 | Abdulziz alqahtani | 18 | 18 | 100% | 2024-01-16 | 0 | 6 | 58 | 59.4286
| Designing the UI design and the interface | 5 | 6 | Ahmed aldayel | Done | 2024-01-17 | Sprint Length | 14 | Ahmed aldayel | 10 | 10 | 100% | 2024-01-17 | 5 | 11 | 53 | 54.8571
| Developing the prototype(coding) | 10 | 12 | Abdulziz alqahtani | Done | 2024-01-21 | Hours Per Day: | 4.5714 | Faisal Batis | 13 | 13 | 100% | 2024-01-18 | 0 | 11 | 53 | 50.2857
| Designing the context diagram and state diagram | 5 | 6 | Abdulziz alqahtani | Done | 2024-01-19 |  |  | Khaled tomihi | 10 | 10 | 100% | 2024-01-19 | 15 | 26 | 38 | 45.7143
| Designing the use case diagram and sequence diagram | 5 | 6 | Faisal Batis | Done | 2024-01-19 |  |  | abdullah Bin Suqaih | 13 | 13 | 100% | 2024-01-20 | 0 | 26 | 38 | 41.1429
| Designing the class diagram and activity diagram | 5 | 6 | Ahmed aldayel | Done | 2024-01-19 |  |  |  | 0 | 0 | 0% | 2024-01-21 | 16 | 42 | 22 | 36.5714
| reviewing the system models | 6 | 8 | Khaled tomihi | Done | 2024-01-21 | [6 empty] | 2024-01-22 | 17 | 59 | 5 | 32
| documentation | 4 | 4 | Khaled tomihi | Done | 2024-01-22 |  |  | Total: | 64 | 64 | 100% | 2024-01-23 | 5 | 64 | 0 | 27.4286
| second phase of coding the prortotype | 8 | 9 | abdullah Bin Suqaih | Done | 2024-01-22 | [6 empty] | 2024-01-24 | 0 | 64 | 0 | 22.8571
| reviewing the prototype and make sure its completed | 5 | 5 | abdullah Bin Suqaih | Done | 2024-01-22 | [6 empty] | 2024-01-25 | 0 | 64 | 0 | 18.2857
| writing the scrum | 5 | 5 | Faisal Batis | Done | 2024-01-23 | [6 empty] | 2024-01-26 | 0 | 64 | 0 | 13.7143
[5 empty] | To Do | [7 empty] | 2024-01-27 | 0 | 64 | 0 | 9.1429
[5 empty] | To Do | [7 empty] | 2024-01-28 | 0 | 64 | 0 | 4.5714
[5 empty] | To Do | [7 empty] | 2024-01-29 | 0 | 64 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 58 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 58 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 53 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 53 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 38 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 38 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 22 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| create the environment for the program | 4 | 6 | Abdulziz alqahtani | Done | 2023-12-28 | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2023-12-25 | 9 | 9 | 45 | 54
| design UI | 8 | 12 | Ahmed aldayel | Done | 2023-12-29 | Start Date: | 2023-12-25 | Abdulziz alqahtani | 15 | 15 | 100% | 2023-12-26 | 9 | 18 | 36 | 49.7857
| tasks development | 5 | 7 | Faisal Batis | Done | 2023-12-25 | Sprint Length | 14 | Ahmed aldayel | 11 | 11 | 100% | 2023-12-27 | 0 | 18 | 36 | 45.5714
| handling the document and the scope of the project | 6 | 6 | Khaled tomihi | Done | 2023-12-26 | Hours Per Day: | 4.2143 | Faisal Batis | 8 | 8 | 100% | 2023-12-28 | 4 | 22 | 32 | 41.3571
| handling the features and objectives and review them | 4 | 4 | abdullah Bin Suqaih | Done | 2023-12-25 |  |  | Khaled tomihi | 11 | 11 | 100% | 2023-12-29 | 8 | 30 | 24 | 37.1429
| design activities for the sprint | 3 | 3 | Faisal Batis | Done | 2023-12-26 |  |  | abdullah Bin Suqaih | 9 | 9 | 100% | 2023-12-30 | 5 | 35 | 19 | 32.9286
| writing and documenting the scrum | 5 | 6 | Faisal Batis | Done | 2024-01-03 |  |  |  | 0 | 0 | 0% | 2023-12-31 | 0 | 35 | 19 | 28.7143
| handling the coding for the initial version of the app | 5 | 5 | Abdulziz alqahtani | Done | 2023-12-30 | [6 empty] | 2024-01-01 | 3 | 38 | 16 | 24.5
| creating the document | 3 | 3 | Ahmed aldayel | Done | 2024-01-01 |  |  | Total: | 54 | 54 | 100% | 2024-01-02 | 6 | 44 | 10 | 20.2857
| continue and complete the coding | 6 | 6 | Abdulziz alqahtani | Done | 2024-01-02 | [6 empty] | 2024-01-03 | 5 | 49 | 5 | 16.0714
| revising the work done so far | 5 | 5 | abdullah Bin Suqaih | Done | 2024-01-04 | [6 empty] | 2024-01-04 | 5 | 54 | 0 | 11.8571
| complete the missing work or the errors found in the revision | 5 | 5 | Khaled tomihi | Done | 2024-01-05 | [6 empty] | 2024-01-05 | 5 | 59 | -5 | 7.6429
[5 empty] | To Do | [7 empty] | 2024-01-06 | 0 | 59 | -5 | 3.4286
[5 empty] | To Do | [7 empty] | 2024-01-07 | 0 | 59 | -5 | 0
[5 empty] | To Do | [7 empty] | 2024-01-08 | 0 | 59 | -5 | 0
[5 empty] | To Do | [8 empty] | 0 | 50 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 41 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 41 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 37 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 29 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 24 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 24 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 15 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 10 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")